## Jira Backlog
Issue Type | User Story / Task | Description | Story Points | Assigned To | Branch Name | Status
Epic | Resume Screening System | Complete end-to-end resume screening platform | 0 | Team Lead | main | To Do
Story | Project Setup | Setup Flask project structure and virtual environment | 3 | Akshit | feature/project-setup | To Do
Story | Resume Upload Module | Upload and validate PDF resumes | 5 | Akshit | feature/resume-upload | To Do
Story | Text Extraction | Extract text from PDF resumes | 5 | Akshit | feature/text-extraction | To Do
Story | Text Preprocessing | Clean and preprocess resume and JD text | 5 | Akshit | feature/text-preprocessing | To Do
Story | TF-IDF Vectorization | Convert text into TF-IDF vectors | 5 | Akshit | feature/tfidf-model | To Do
Story | Cosine Similarity | Calculate similarity scores | 3 | Akshit | feature/cosine-similarity | To Do
Story | BERT Integration | Implement BERT-based similarity | 8 | Akshit | feature/bert-model | To Do
Story | Resume Ranking | Rank resumes based on scores | 3 | Akshit | feature/resume-ranking | To Do
Story | UI Development | Design frontend using HTML/CSS/Bootstrap | 5 | Akshit | feature/ui-design | To Do
Story | Result Display | Show ranked resumes with scores | 3 | Akshit | feature/result-display | To Do
Story | Error Handling | Handle invalid files and edge cases | 3 | Akshit | feature/error-handling | To Do
Story | Deployment on Render | Deploy Flask app on Render | 5 | Akshit | feature/render-deployment | To Do
Story | Testing | Unit and integration testing | 5 | Akshit | feature/testing | To Do
Story | Documentation | Prepare SRS and project documentation | 3 | Akshit | feature/documentation | To Do